## Cover
Requirements Pack
Patient No-Show Risk Flagging & Intervention
Author | Nityam Sharma — Business Analyst
Version | 1.0
Domain | Healthcare / Patient Access & Scheduling
Contents | User Stories · Requirements Traceability Matrix · UAT Plan
Companion docs | Problem Brief, BRD, FRD (Markdown in /docs)
Coverage summary (row counts per tab)
User stories | 11
Business requirements traced | 11
'Must' requirements | 8
UAT test cases | 11

## User Stories
Story ID | Epic | As a / I want / So that | Priority | Points | Traces To | Acceptance Criteria (Given/When/Then)
US-01 | 1 Risk Scoring | As a scheduling system, I want to score no-show risk at booking, so that staff can act before the appointment. | Must | 5 | BR-001, FR-101 | AC1: Given a new appointment saved, then a score+tier are stored before confirmation. AC2: Scoring completes < 2s.
US-02 | 1 Risk Scoring | As an operations lead, I want each appointment labelled Low/Medium/High, so that the right intervention applies. | Must | 3 | BR-002, FR-102/104 | AC1: 0-1 pts=Low, 2-4=Medium, 5+=High. AC2: Exactly one tier per appointment.
US-03 | 1 Risk Scoring | As a BA, I want scoring to use lead time, prior history, age band, welfare, chronic flags, so that it reflects real drivers. | Must | 5 | BR-003, FR-103/402 | AC1: All five feature groups contribute per FRD rules. AC2: Missing feature defaults to 0 and is logged.
US-04 | 1 Risk Scoring | As a compliance reviewer, I want transparent, stored scoring, so that decisions are auditable. | Should | 3 | BR-011, FR-105 | AC1: Feature values, points, tier persisted on the record. AC2: Rule version identifiable.
US-05 | 2 Intervention | As a scheduling system, I want appointments routed to the workflow for their tier, so that effort matches risk. | Must | 5 | BR-004, FR-201 | AC1: Low->single T-1 reminder. AC2: Medium->T-3 & T-1 cadence. AC3: High->call task + confirm SMS.
US-06 | 2 Intervention | As a front-desk agent, I want high-risk appointments to raise a call task, so that I confirm the riskiest patients. | Must | 5 | BR-005, FR-204/205 | AC1: Call task appears in queue for High. AC2: Unconfirmed in window -> eligible for controlled overbooking.
US-07 | 2 Intervention | As an ops admin, I want to configure reminder timings without a release, so that we can tune cadence. | Should | 3 | BR-006, FR-206 | AC1: Changed timing applies to new appointments with no deployment.
US-08 | 3 Dashboard | As a clinic manager, I want no-show rate by tier/lead/age/welfare/clinic, so that I know where to focus. | Must | 5 | BR-007, FR-301/302 | AC1: KPI + volume for the period. AC2: All five breakdowns available.
US-09 | 3 Dashboard | As a patient-access director, I want a rolling 90-day trend vs target, so that I can track whether it's working. | Must | 3 | BR-008, FR-303 | AC1: Rolling 90-day rate with a configurable target line.
US-10 | 3 Dashboard | As a patient-access director, I want the welfare no-show gap surfaced, so that interventions don't widen inequity. | Should | 2 | BR-010, FR-304 | AC1: Welfare vs non-welfare rate shown side by side as a gap.
US-11 | 4 Data/Quality | As a data engineer, I want cleaning rules DQ-1..7 applied before scoring, so that scores use valid data. | Must | 5 | BR-009, FR-401/403 | AC1: Invalid age / negative lead rejected and logged, not scored. AC2: Columns standardized, inverted label corrected.

## RTM
Business Req | Description | Functional Req | User Story | UAT Test Case | Priority | Status
BR-001 | Score every appointment at booking | FR-101, FR-106 | US-01 | UAT-01 | Must | Ready for build
BR-002 | Classify Low/Medium/High | FR-102, FR-104 | US-02 | UAT-02 | Must | Ready for build
BR-003 | Use agreed risk features | FR-103, FR-402 | US-03 | UAT-03 | Must | Ready for build
BR-004 | Route to intervention tier | FR-201, FR-202 | US-05 | UAT-05 | Must | Ready for build
BR-005 | High-risk confirmation + overbooking | FR-204, FR-205 | US-06 | UAT-06 | Must | Ready for build
BR-006 | Medium-risk multi-touch cadence | FR-203, FR-206 | US-07 | UAT-07 | Should | Ready for build
BR-007 | Dashboard breakdowns | FR-301, FR-302, FR-305 | US-08 | UAT-08 | Must | Ready for build
BR-008 | 90-day trend vs target | FR-303 | US-09 | UAT-09 | Must | Ready for build
BR-009 | Data-quality rules before scoring | FR-401, FR-403 | US-11 | UAT-11 | Must | Ready for build
BR-010 | Equity (welfare) gap indicator | FR-304 | US-10 | UAT-10 | Should | Ready for build
BR-011 | Transparent, auditable scoring | FR-104, FR-105 | US-04 | UAT-04 | Should | Ready for build

## UAT Plan
Test ID | Traces To | Scenario | Preconditions | Steps (When) | Expected Result (Then) | Priority | Status
UAT-01 | US-01 / BR-001 | Score generated at booking | User can create appointments | Create a new appointment and save | Risk score + tier stored before confirmation; scoring < 2s | Must | Not Run
UAT-02 | US-02 / BR-002 | Correct tier boundaries | Scoring engine live | Book appts engineered to 1, 3, and 6 points | Tiers returned are Low, Medium, High | Must | Not Run
UAT-03 | US-03 / BR-003 | All features contribute | Scoring engine live | Book 30+ day-lead, age-25, welfare patient w/ prior no-shows | Score reflects lead+age+welfare+history -> High | Must | Not Run
UAT-04 | US-04 / BR-011 | Score is auditable | Appointment scored | Open the appointment audit view | Feature values, points, tier, rule version visible | Should | Not Run
UAT-05 | US-05 / BR-004 | Routing matches tier | Scoring + workflow live | Book one Low, one Medium, one High appointment | Low->single reminder; Medium->T-3&T-1; High->call+confirm SMS | Must | Not Run
UAT-06 | US-06 / BR-005 | High-risk confirmation & overbooking | High appt unconfirmed | Let confirmation window lapse | Flagged eligible for controlled overbooking; call task present | Must | Not Run
UAT-07 | US-07 / BR-006 | Configurable cadence | Admin access | Change Medium cadence T-3 -> T-4 and save | New Medium appts use T-4; no deployment | Should | Not Run
UAT-08 | US-08 / BR-007 | Dashboard breakdowns | Dashboard live, data loaded | Open dashboard for a period | KPI + breakdowns by tier, lead, age, welfare, clinic render | Must | Not Run
UAT-09 | US-09 / BR-008 | 90-day trend vs target | Dashboard live | Open trend view | Rolling 90-day trend with configurable target line | Must | Not Run
UAT-10 | US-10 / BR-010 | Equity indicator | Dashboard live | View equity panel | Welfare vs non-welfare rates shown as a gap | Should | Not Run
UAT-11 | US-11 / BR-009 | Data-quality enforcement | Pipeline live | Feed age=-1 and a negative lead-time record | Both rejected and logged; valid records processed | Must | Not Run